## Project Tracker
Project Tracker & Gantt
SME Intelligence — Track tasks, deadlines, assignments and progress. Gantt chart auto-generates.
Project Name: |  |  |  |  | Start Date:
Project Manager: |  |  |  |  | Target End:
# | Task | Owner | Priority | Status | Start Date | Due Date | Days | % Complete | Dependencies | Notes
1 | Project kickoff & planning | Peter | Critical | Complete | 2026-01-06 | 2026-01-10 |  | 100% |  | Define scope and timeline
2 | Requirements gathering | Alice | High | Complete | 2026-01-13 | 2026-01-24 |  | 100% | 1 | Stakeholder interviews
3 | UI/UX design mockups | Bob | High | In Progress | 2026-01-27 | 2026-02-07 |  | 60% | 2 | Figma wireframes
4 | Database schema design | Peter | High | In Progress | 2026-01-27 | 2026-02-03 |  | 80% | 2 | PostgreSQL
5 | Backend API development | Peter | Critical | Not Started | 2026-02-10 | 2026-03-07 |  | 0% | 3,4 | REST API endpoints
6 | Frontend development | Alice | High | Not Started | 2026-02-17 | 2026-03-14 |  | 0% | 3 | React components
7 | Integration testing | Bob | High | Not Started | 2026-03-17 | 2026-03-28 |  | 0% | 5,6 | End-to-end tests
8 | User acceptance testing | Alice | Medium | Not Started | 2026-03-31 | 2026-04-11 |  | 0% | 7 | Client sign-off
9 | Deployment & go-live | Peter | Critical | Not Started | 2026-04-14 | 2026-04-18 |  | 0% | 8 | Production deploy
10 | Post-launch support | Bob | Medium | Not Started | 2026-04-21 | 2026-05-02 |  | 0% | 9 | Bug fixes & monitoring
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Summary
Project Summary
Total Tasks
Complete
In Progress
Not Started
Blocked
Overall Progress

## Gantt Chart
Gantt Chart
Auto-generated from Project Tracker dates
Task | Status | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01
Legend: |  |  | Complete |  | In Progress |  | Not Started |  | Blocked